## Sheet1
"Lofthus" - Gantt Chart
Task | Start | End | Duration | Responsible | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
[5 empty] | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15
REQUIREMENTS | 2020-08-10 | 2020-09-04 | 20 | bar: Week 1 10 to Week 4 4
*Collect client's vision and goals | 2020-08-10 | 2020-08-14 | 5 | Manager/UI Designer | bar: Week 1 10 to Week 1 14
*Review brandmarks of client's product | 2020-08-12 | 2020-08-17 | 4 | Manager/UI Designer | bar: Week 1 12 to Week 2 17
*Reserch brands | 2020-08-13 | 2020-08-26 | 10 | Manager/UI Designer | bar: Week 1 13 to Week 3 26
*Draft concept | 2020-08-25 | 2020-08-28 | 4 | Manager/UI Designer | bar: Week 3 25 to Week 3 28
*Modify/adjust brand strategy | 2020-08-25 | 2020-08-28 | 4 | Manager/UI Designer | bar: Week 3 25 to Week 3 28
*Draft creative brief | 2020-08-26 | 2020-08-28 | 3 | Manager/UI Designer | bar: Week 3 26 to Week 3 28
*Client approval for layout concept | 2020-08-31 | 2020-09-04 | 5 | bar: Week 4 31 to Week 4 4
*Sprint review | 2020-09-04 | 2020-09-04 | 1 | Team
DESIGN | 2020-09-02 | 2020-09-18 | 13 | bar: Week 4 2 to Week 6 18
*Drawings | 2020-09-02 | 2020-09-11 | 8 | Graphic D | bar: Week 4 2 to Week 5 11
*Color&Graphics | 2020-09-09 | 2020-09-11 | 3 | Graphic D. | bar: Week 5 9 to Week 5 11
*Fonts (colors, sizes) | 2020-09-11 | 2020-09-15 | 3 | Graphic D. | bar: Week 5 11 to Week 6 15
*Content wrting and assembly | 2020-09-09 | 2020-09-18 | 8 | Copywriter | bar: Week 5 9 to Week 6 18
*Sprint review | 2020-09-18 | 2020-09-18 | 1 | Team
CONSTRUCTION | bar: Week 6 16 to Week 9 9
*Development | 2020-09-16 | 2020-10-06 | 15 | Fron-end | bar: Week 6 16 to Week 9 6
*Multimedia | 2020-09-21 | 2020-10-06 | 12 | Front-end | bar: Week 7 21 to Week 9 6
*Functionality | 2020-09-21 | 2020-10-06 | 12 | Front-end | bar: Week 7 21 to Week 9 6
*Beta testing and review | 2020-10-05 | 2020-10-09 | 5 | Front-end | bar: Week 9 5 to Week 9 9
*Browser compatibility (Safari, Chrome, Firefox) | 2020-10-07 | 2020-10-09 | 3 | Front-end | bar: Week 9 7 to Week 9 9
*Sprint review | 2020-10-09 | 2020-10-09 | 1 | Team
IMPLEMENTATION | 2020-10-12 | 2020-10-15 | 4 | Team | bar: Week 10 12 to Week 10 15